## Overview
SME Zero Trust Implementation Workbook
From Secureware. — Cybersecurity Auditing for the UK & USA
About this workbook
A 90-day implementation plan for SME organisations adopting Zero Trust principles without enterprise-scale tooling budgets. Built around three pillars: identity, network segmentation, and device trust. Targets a total budget of £3,000 / ~$3,800 in one-time investment plus modest ongoing costs.
Workbook contents
1. Overview — This page — orientation and instructions
2. 90-Day Plan — Week-by-week implementation tasks with owners and status
3. Identity Checklist — Universal MFA, Conditional Access, PIM, account hygiene
4. Network Checklist — VLAN design, WireGuard, segmentation rules
5. Device Checklist — Intune enrolment, compliance policies, EDR baselining
6. Cost Calculator — Customisable budget model — adjust headcount and unit costs
7. Risk Register — Tracking template for residual risks during implementation
Usage
Yellow cells are inputs — customise to your organisation. Other cells use formulas and update automatically. The Cost Calculator drives the total budget figure on the 90-Day Plan.
Licence
© Secureware. 2026 — Free for client use. Not for redistribution.

## 90-Day Plan
Week | Task | Detail | Owner | Status | Est Cost (£)
Week 1 | Universal MFA enforcement | Configure Conditional Access to require MFA for all users. No exceptions. Verify no service accounts are exempt. | Identity Lead | Not Started | 0
Week 1 | Disable legacy authentication | Conditional Access policy blocking legacy auth protocols (POP, IMAP, basic auth). | Identity Lead | Not Started | 0
Week 2 | Account hygiene audit | Disable unused accounts. Audit admin role assignments. Reduce permanent admin assignments. | Identity Lead | Not Started | 0
Week 2 | Enable PIM (Privileged Identity Management) | Configure time-limited elevation for admin roles. Eliminate permanent global admin assignments. | Identity Lead | Not Started | 0
Week 3-4 | Conditional Access fine-tuning | Device compliance policy. Location-based policies. Block high-risk sign-ins. | Identity Lead | Not Started | 0
Week 5 | Procure managed switch hardware | Select switches based on Cost Calculator. Order with 2-week lead time buffer. | Network Lead | Not Started | 1200
Week 6 | VLAN design and configuration | Configure VLANs: Corporate, IoT/CCTV, Guest WiFi, Servers, Management. Document inter-VLAN ACLs. | Network Lead | Not Started | 0
Week 6 | Guest WiFi isolation | Verify guest WiFi cannot reach corporate VLAN. Test from guest device. | Network Lead | Not Started | 0
Week 7 | WireGuard VPN deployment | Stand up WireGuard server. Issue device-bound peer configurations. Decommission legacy VPN. | Network Lead | Not Started | 100
Week 8 | Network segmentation testing | Penetration test against new segmentation. Verify lateral movement is contained. | Network Lead | Not Started | 0
Week 9 | Intune enrolment — Windows | Auto-enrol all Windows devices in Intune. Configure compliance policies. | Device Lead | Not Started | 0
Week 9 | Intune enrolment — Mac/iOS/Android | Enrol Mac, iPhone, iPad, Android devices. Per-platform compliance policies. | Device Lead | Not Started | 0
Week 10 | Conditional Access — device compliance | Block non-compliant devices from accessing M365 applications. | Identity Lead | Not Started | 0
Week 11 | SIEM deployment | Microsoft Sentinel or Elastic SIEM. Connect M365, Entra ID, Intune, Defender. | Security Lead | Not Started | 100
Week 12 | Detection rules and runbooks | Deploy high-fidelity detection rules. Document incident response runbooks. | Security Lead | Not Started | 0
Week 13 | Final review and documentation | Document architecture. Brief leadership. Establish quarterly review cadence. | Security Lead | Not Started | 0
| Total one-time estimate |  |  |  | 1400
Status summary
| Completed | 0
| In Progress | 0
| Not Started | 16
| Completion % | 0%

## Identity Checklist
# | Control | Status | Evidence / Notes
1 | MFA enforced on all user accounts via Conditional Access | ☐ Not done
2 | MFA enforced on all admin accounts via dedicated policy | ☐ Not done
3 | Legacy authentication blocked at tenant level | ☐ Not done
4 | Conditional Access blocking sign-ins from unexpected geographies | ☐ Not done
5 | Conditional Access requiring compliant device for sensitive apps | ☐ Not done
6 | Privileged Identity Management enabled for admin role activation | ☐ Not done
7 | Permanent global admin assignments minimised (target: 0) | ☐ Not done
8 | Break-glass accounts documented and tested | ☐ Not done
9 | Service accounts inventory complete and reviewed quarterly | ☐ Not done
10 | Service account passwords rotated; gMSA used where supported | ☐ Not done
11 | Sign-in risk policies configured (high-risk sign-ins blocked) | ☐ Not done
12 | User risk policies configured (compromised accounts force password change) | ☐ Not done
13 | Guest user reviews running quarterly | ☐ Not done
14 | External collaboration policies aligned with data classification | ☐ Not done
15 | Application consent restrictions configured (admin consent workflow) | ☐ Not done
16 | Self-service password reset enabled with security questions disabled | ☐ Not done
17 | Password protection (banned password list) configured | ☐ Not done
18 | Hardware security keys issued for highest-privilege accounts | ☐ Not done

## Network Checklist
# | Control | Status | Evidence / Notes
1 | VLAN segmentation deployed (Corporate, IoT, Guest, Servers, Management) | ☐ Not done
2 | Inter-VLAN ACLs configured restricting cross-VLAN access | ☐ Not done
3 | Guest WiFi isolated from corporate VLAN — tested from guest device | ☐ Not done
4 | Management VLAN accessible only from dedicated admin workstation | ☐ Not done
5 | Server VLAN accessible only from Corporate VLAN on specific ports | ☐ Not done
6 | IoT VLAN cannot reach Corporate VLAN | ☐ Not done
7 | WireGuard VPN deployed for remote access | ☐ Not done
8 | Legacy VPN (OpenVPN, L2TP) decommissioned | ☐ Not done
9 | Device-bound WireGuard configurations issued per user | ☐ Not done
10 | MFA enforced on VPN access via Conditional Access | ☐ Not done
11 | Switch management interfaces accessible only from Management VLAN | ☐ Not done
12 | Firewall logs forwarded to SIEM | ☐ Not done
13 | DNS filtering or DNS-over-HTTPS deployed | ☐ Not done
14 | External attack surface mapped and documented | ☐ Not done
15 | Penetration test conducted against segmentation | ☐ Not done

## Device Checklist
# | Control | Status | Evidence / Notes
1 | All Windows devices enrolled in Intune | ☐ Not done
2 | All macOS devices enrolled in Intune | ☐ Not done
3 | All corporate-issued iOS devices enrolled | ☐ Not done
4 | All corporate-issued Android devices enrolled | ☐ Not done
5 | Personal device (BYOD) policy defined and documented | ☐ Not done
6 | Device compliance policy: OS updates current | ☐ Not done
7 | Device compliance policy: full disk encryption | ☐ Not done
8 | Device compliance policy: endpoint protection running | ☐ Not done
9 | Device compliance policy: screen lock + minimum password complexity | ☐ Not done
10 | Conditional Access blocking non-compliant devices | ☐ Not done
11 | Microsoft Defender for Business deployed | ☐ Not done
12 | Defender ASR (Attack Surface Reduction) rules in audit then enforce | ☐ Not done
13 | USB device control policy | ☐ Not done
14 | Bitlocker recovery keys backed up to Entra ID | ☐ Not done
15 | Device wipe procedure documented and tested | ☐ Not done

## Cost Calculator
Cost Calculator
Adjust the yellow cells to reflect your organisation
Inputs
Headcount | 25
M365 Business Premium £/user/month | 18
Managed switch unit cost (£) | 250
Number of switches required | 4
WireGuard VPS £/month | 5
Microsoft Sentinel £/month (estimated) | 60
Penetration test £ (annual) | 4500
One-time costs
Managed switches | 1000
Initial configuration consulting (estimate 5 days @ £800) | 4000
Initial penetration test (validation) | 4500
One-time total | 9500
Annual recurring costs
M365 Business Premium licences | 5400
WireGuard VPS | 60
Microsoft Sentinel | 720
Annual penetration test | 4500
Annual total | 10680
Per-user cost
One-time per user | 380
Annual per user | 427.2
Year 1 total per user | 807.2

## Risk Register
ID | Risk Description | Likelihood | Impact | Score | Mitigation | Status | Owner
R1 | User pushback against MFA enforcement disrupting business operations | 3 | 3 | 9 | Open | Identity Lead
R2 | Legacy application breaks due to legacy authentication block | 3 | 3 | 9 | Open | Identity Lead
R3 | VLAN misconfiguration causes production service outage | 2 | 4 | 8 | Open | Network Lead
R4 | Intune compliance policy blocks legitimate business operations | 3 | 2 | 6 | Open | Device Lead
R5 | SIEM alert fatigue causes real incidents to be missed | 4 | 4 | 16 | Open | Security Lead
R6 | WireGuard VPN deployment leaves remote staff without access | 2 | 4 | 8 | Open | Network Lead
R7 | Project lead leaves mid-implementation | 2 | 3 | 6 | Open | Programme Manager
Score legend
Likelihood: 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost Certain
Impact: 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Severe
Score: Likelihood × Impact (1-25)